## Sheet1
Project Timeline
Week of:
| Nov. 17 | Nov. 24 | Dec. 1 | Dec. 8
Implementation
Frame Correction System
Transform Module | Ganesh
Manual Override |  | Ganesh
Audio System
Track Playback | Shawn
Triggering System |  | Shawn
Accelerometer
SPI Interface | James
Normalizing and Denoising Data | James
Tilt Angle Estimation | James
Camera |  | James & Shawn
Integration
Accelerometer to Frame Correction |  | James & Ganesh
Audio System Triggers |  | James & Shawn & Ganesh
Testing
Frame Correction System |  | Ganesh
Audio System |  | Shawn
Accelerometer |  | James
Camera |  |  | James & Shawn
System-Integration Testing |  |  | James & Shawn & Ganesh